## Sheet1
Achievement | Num | Progress | Duration |  |  |  |  | Stakeholder communication | IsMilestone
|  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Achievement 1 | 1 | Make project management plan
| 1.1 | Make project schedule and set milestone
| 1.2 | Video call with all stakeholders to discuss the project management plan | [5 empty] | ✆
| 1.3 | Revise the project management plan
| 1.4 | Email and confirm the project management plan to all stakeholders | [5 empty] | 📧 | ⚐
| 2 | Calculate historical flu shot rates and verify relationship with fatality
| 2.1 | Calculate historical flu shot rates for all states
| 2.2 | Conduct data analysis to verify the relationship with fatality, including iteration
| 2.3 | Report (email) report project progress to all stakeholders | [5 empty] | 📧 | ⚐
| 3 | Make staffing plan for medical staffing agency
| 3.1 | Conduct a predicted data analysis for this coming influenza season
| 3.2 | Draft staffing plan according to the data prediction
| 3.3 | Video call with all stakeholders to discuss the staffing plan | [5 empty] | ✆
| 3.4 | Iterate the staffing plan | [6 empty] | ⚐
Achievement 2 | 4 | Complete final report
| 4.1 | Design and build visualized data findings according to previous data analysis
| 4.2 | Combine the visualized data and the staffing plan into a PPT report
| 4.3 | Prepare a detailed doc to support the PPT report for stakeholders reference
| 4.4 | Video call with all stakeholders to present my final report | [5 empty] | ✆ | ⚐